## Slide 1: ESP KPI Tracker Update
Jan 5 2026

## Slide 2: Agenda
Introductions
Project Goals and Objectives
Project Status Update
  Work Completed
  Status %
  Timeline and Resourcing
  Demo
Upcoming Tasks

## Slide 3: Project Goals and Objectives (WIP)
Goal
Objectives
Value to CNRL

## Slide 4: What’s Been Completed & What’s Next
Completed Work
  Core UI, database and ETL delivered in Feb 2025
  Data optimized and reporting dashboards launched
  Change requests addressed (expanded in later slides)
Current Focus
  Integration with external vendors
  Ongoing user adoption and training
  Visualization development
Upcoming Tasks
  Next round of visualizations
  System stabilization and scaling
Wayne

## Slide 5: ESP KPI Tracking Project –Feb 2025
VP / Manager
Tableau/PowerBi
Excel
Oracle
Web Input Forms
Project Overview to Show Major Areas of Development
⋮
Database
Existing Excel Tool
ETL
Q/C.
Reports
Quarterly: Presentation
Monthly: Report 1-page
Specials: Budget Report 1-page
ETL: Extract/Transform/Load
using Stored Procedure/Knime
Analytics
Vendor Entry
CNRL Entry
Field and
Calgary
Wayne
90%
75%
95%
50%
20%

## Slide 6: ESP KPI Tracking Project – Dec 2025
VP / Manager
PowerBi
Excel
Oracle
Web Input Forms
Project Overview to Show Major Areas of Development
⋮
Database
Existing Excel Tool
ETL
Q/C.
Reports
Annual: Presentation
Monthly: Report 1-page
Budget Report 1-page
Shroud 1-page
ETL: Extract/Transform/Load
using Stored Procedure
Analytics
Vendor Entry
CNRL Entry
Field and
Calgary
Wayne
98% + added Enhancements (2% pending vendor rollout)
100%
100%
80%
25%
95%
Completed Using Excel
Completed Using Excel

## Slide 7: Project Timeline & Key Milestones
Delays:
  Resourcing constraints
  Shifting organizational priorities
  UAT testing extensions
  Team re-assignments
Upcoming Milestones:
  Vendor onboarding: Jan 2026
  Project completion: Mar 2026
Wayne
Feb 2023 Kickoff
Feb 2025 Prod
Jan 2026 Vendors
Mar 2026 Complete

## Slide 8: 2025 Web App Development & Testing Achievements
Erika
User Acceptance Testing (UAT)
  Completed 6 sessions with internal user groups
  Logged and implemented ~50 enhancements
Beta Testing
  Conducted 3-week beta program
  Logged and implemented ~25 additional enhancements
Notes: In 2025, we conducted extensive testing across all internal user groups. Feedback was overwhelmingly positive, and we identified approximately 75 minor enhancements. These included adjustments to field labels, units of measurement, and field ordering to improve usability and workflow. All requested changes were prioritized and successfully implemented, ensuring a smoother user experience.

## Slide 9: 2025 Web App Development Achievements & Demo
Erika
External-Facing Application Security
  Secured PWA with PingID (CNRL standard sign-in)
  Preserved data integrity via automated form locking for vendors
  Restricted form access and editability by user role
User Experience Improvements
  Streamlined workflow for adding equipment installs to a Production Period
  Added data-loss prevention features with easy rollback options
Demo Links:
  https://devapp.cnrl.com/espkpitracker/
  https://desktop.pingone.com/cnrl/Selection?cmd=selection
Notes: Following UAT, we focused on improving workflows—particularly the process of adding new part numbers, equipment, and then installing them in a production period. These changes significantly reduced complexity and improved efficiency.
We also addressed a major pain point: accidental data loss. Users now receive prompts if they attempt to leave without saving, and we introduced a persistent master save button that is always visible, making it easy to locate and use. These enhancements provide a safety net and improve overall usability.

## Slide 10: 2025 Features & Demo (Part 2)
Erika
File Downloading Functionality
  Added printable versions of forms for offline data capture
  Standardized layout to align with PWA flow
Advanced Admin Functions
  Enabled front-end management of dropdown lists
  Eliminated need for IS involvement in routine updates
Notes: We introduced printable versions of the forms to allow users to capture required data offline and then easily transfer it into the PWA. These forms mirror the PWA layout to maintain consistency and reduce errors. To further guide users, we added color-coded sections indicating responsibility for each data field.
Additionally, we built advanced admin functionality, including a dropdown management tab. This empowers the business to manage and update dropdown lists directly from the front end—without requiring IS support—giving teams more flexibility and control.

## Slide 11: 2025 Data Integration Achievements
Emily
ETL Status
  Complete through October 9th
  Supporting Data Added
    Part number descriptions
    CNRL equipment inventory
Data Cleanup
  Validated and standardized spreadsheet data before and during ETL
  Corrected nonstandard values to ensure consistency
Reporting Views
  KPI tracker views available for dashboard creation
  Collaborated with Cam and Shane to resolve data inconsistencies
Notes: Our ETL process is now complete through October 9th, ensuring that all critical data is up to date. We’ve added supporting datasets, including part number descriptions and CNRL’s full inventory of equipment, to enhance reporting accuracy.
Before and during ETL, we performed rigorous data cleanup—validating spreadsheets, standardizing formats, and correcting nonstandard values. This proactive approach minimized errors and improved overall data integrity.
To support reporting, KPI tracker views are now available for dashboard creation, giving teams real-time visibility into key metrics. We also collaborated closely with Cam and Shane to resolve data inconsistencies, ensuring a reliable foundation for analytics and decision-making.

## Slide 12: Power Bi Dashboard Development
Monthly Reporting
  Replicate monthly report from excel ESP tracker
  WKO/Equipment costs
  Activity compared to budget
Reliability Benchmarking
  Run times
  MTTF
  Survival curve
Leading ESP Failures
  Failed component
  Vendor
  Cause of failure
Cam
Link to Dashboards
Notes: The main dashboard is replicated from the excel tracker monthly report
Creating this dashboard requires the creation of equations that can be validated by the original report
The new monthly report dashboard is also dependent on data validation (Cost graph example)
Examples like this help find data quality issues
Can easily PDF a report like this for management
R:\Thermal\SH\SSEng\Kirby\Production Ops\SubSurf Equip & Design\Artificial Lift\ESP\ESP Reports\ESP Tracker PowerBi

## Slide 13: Power Bi Dashboard Development - Challenges
Dashboard
  Improving small details on the dashboard
    Linking slicers to correct visualizations without affecting others
    Cleaning up data (changing formats and decimal places)
  Making dashboard more intuitive for users
Data
  Data is not fully up to date for required visuals, making it difficult to verify calculations vs data issues
  No Failure Date data until early December
Time
  Gaining experience using Power BI takes extra time
Cam

## Slide 14: Power Bi Dashboard Development - Next Steps
Refine and publish current dashboards
  Add budget info to visuals on monthly report
  Clean up small formatting issues
Current dashboard suggestions
  Shroud reliability monthly update dashboard
Continue to make more dashboards based on
  ESP tracker excel sheet visuals
  Suggestions from others
Cam
Notes: Suggestions
Duplicate ESP health/data excel sheet (Link)
Access/Create budget table to include on various dashboards (similar to WKO budget?
Include physical tracker table and make it filterable
Check out CFER Powerbi
ESP Presentation: Link
Shanes list from email
  Activity (by field, date, vendor, equipment model)
    Installs
    Pulls,
    Failures
    Non- Failure pulls
    Active / Running
  Reliability:
    Premature ESP Failures (<365 days runtime)
    Failure rates (run day / fail)
    MTTF (fails / total runtime)
    Average Run Time (days)
      Non Failed
      Failed (run time failed pumps / total failures)
      Running (run time of pumps /running pumps)
      Pulled (run time pulled pumps / total pumps pulls)
    Survival rate ( see this tab Survival TBL_1 (Pre)
  Spend:
    Monthly Spend
    ESP Total
    Average ESP
    WKOr Average
  Tabs:
    Chrt_Rel_MTTF_Field
    Monthly Report
    Survival TBL_1 (Pre)
    Survival TBL_1 (Post)
  Link,
  \\cnrl.com\cnrl\secure\cgy-secure01\Thermal\SH\Library\Consortiums & JIPs\SAGDProducers Forum

## Slide 15: Q1 2026: Transition & Go-Live Activities (WIP)
Focus:
  Full user adoption & system integration by Q1
  Training completion & user manual distribution
  Onboard E&I Eng, Field, Prod Eng
  2026 quotes/design/data loaded into ESP KPI
  Vendor data entry begins Jan 2026
Key Transition Milestones:
  Finish data backfill
  Execute change management plan
  Compliance & utilization tracking (PWA/DB)
  Stakeholder communications
Shane

## Slide 16: Data Scope & Quality Initiatives
Acquire & integrate operational/KPI data
Clean and validate for accuracy/completeness
Apply business rules for consistency
Backfill historical records as needed
Ensure dashboard/reporting readiness
Shane

## Slide 17: 2026 Next Steps: Web Input Forms & Expansion
Commercial adoption & rollout
Continuous improvement from vendor/field feedback
Product evolution and feature growth
  Expand visualization and reporting capabilities
  Look at mobile access and enhanced input forms
  Investigate predictive analytics and automation
Wayne

## Slide 18: CNRL User Adoption Update
Shane